## 2026
| Project | Category | Engineer | Vendor | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
B2B | Lanky | Room bar | Sam Kuan | Amtran | [12 empty] | 0.2 | 0.2 | 0.2 | 0.1 | 0.1
| Cranky | Table Camera | Sam Kuan | TBD | [12 empty] | 0.2 | 0.2 | 0.3
| Kiddy / Kiddo | PTZ Camera | Sam Kuan | Chicony
| Weedle | Accessories | Sam Kuan | CWT | [12 empty] | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
| Gen2Mounts- In wall mount | Accessories | Sam Kuan | TBD | [12 empty] | 0.1 | 0.1 | 0.1 |  |  | 0.1 | 0.1
| Dread | System | Sam Kuan | TBD
| [TB] Evaluate the feasibility of integrating an active thermal solution in Lanky. |  | Sam Kuan | [13 empty] | 0.1 | 0.1 | 0.1
| [TB] CPU–GPU–CDSP Power Distribution and Thermal Performance Evaluation |  | Sam Kuan | [13 empty] | 0.1 | 0.1 | 0.1
| [TB] Using Burn-In Warm-Up Time Constant to Verify Thermal Path & Assembly Quality |  | Sam Kuan | [13 empty] | 0.1 | 0.1 | 0.1
| [Cranky] SoC platform - Ambarella CV5 |  | Sam Kuan | [13 empty] | 0.1 | 0.1 | 0.1
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1.1 | 0.2 | 0.2 | 0.2 | 0.2 | 0 | 0 | 0 | 0 | 0
B2B | Goomba | Mic | Vincent Chen | TYMPHANY | 0.1 | 0.1 | 0.1 | [9 empty] | 0.2 | 0.1 | 0.1 | 0.1 | 0.1
| Nitendo 2 | Accessories | Vincent Chen | FIH | [12 empty] | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
| Artari 2 | Accessories | Vincent Chen | FIH | [12 empty] | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
| Cranky | Table Camera | Vincent Chen | TBD | [15 empty] | 0.6 | 0.6
| Swanky | Room bar | Vincent Chen | TBD | [12 empty] | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6
| Gen2Mounts- In wall mount | Accessories | Vincent Chen | TBD | [15 empty] | 0.1 | 0.1
| Active Thermal Solution |  | Vincent Chen | [13 empty] | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
[5 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 1.1 | 1 | 1 | 1.7 | 1.7 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9
[5 empty] | Room Sys | New | 0.4 / 0.3 | 0.3 | 0.1
[6 empty] | Extension | 0.2 / 0.1 | 0.1 | 0.1
L4B Vision Project Planning | Dread | AIO |  |  | Webcam | New | 0.3 | 0.2 | 0.1
| Artari 2600 | Accessories |  |  |  | Extension | 0.1 | 0.1 | 0.1
| N64 | Accessories
ODM / Alternative Source Project
[7 empty] | PFE | PB1 | PB2
[5 empty] | Room Sys | New | 0.2 / 0.1 | 0.1 | 0.1
[6 empty] | Extension | 0.1 | 0.1 | 0.1
[5 empty] | Webcam | New | 0.2 / 0.1 | 0.1 | 0.1
[6 empty] | Extension | 0.1 | 0.1 | 0.1

## 2025
| Project | Category | Engineer | Vendor | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
B2B | Lanky | Room bar | Sam Kuan | Amtran | [12 empty] | 0.2 | 0.2 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.3 | 0.3 | 0.2 | 0.2
| Cranky | Table Camera | Sam Kuan | TBD | [12 empty] | Perental Leave
| Kiddy / Kiddo | PTZ Camera | Sam Kuan | Chicony | [22 empty] | 0.2 | 0.2
| Weedle | Accessories | Sam Kuan | TBD | [22 empty] | 0.1 | 0.1
| Dread | System | Sam Kuan | TBD
Techno Bricks | Competitor Product Analysis |  | Sam Kuan | [15 empty] | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
| [Lanky] environmental sensor calibration |  | Sam Kuan | [16 empty] | 0.2 | 0.2 | 0.2 | 0.2 | 0.2
| [Cranky] Thermal Design |  | Sam Kuan | [16 empty] | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2
| [TB] Evaluate the feasibility of integrating an active thermal solution in Lanky. |  | Sam Kuan | [22 empty] | 0.2 | 0.1 | 0.1
| [TB] Via Filling Paste |  | Sam Kuan | [22 empty] | 0.1
| [Cranky] SoC platform - Ambarella CV5 |  | Sam Kuan | [18 empty] | 0.1 | 0.1 | 0.1 | 0.1 |  | 0.1 | 0.1
PWS | Kahlo |  | Sam Kuan | In house | [17 empty] | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.2 | 0.2 | 0.5 | 0.9 | 0.9 | 1.1 | 1.1 | 1.1 | 0.8 | 1 | 1 | 1
B2B | Dixie | Board | Vincent Chen | Amtran | [12 empty] | 0.4 | 0.1
| Goomba | Mic | Vincent Chen | TYMPHANY | 0.1 | 0.1 | 0.1 | [9 empty] | 0.5 | 0.5 | 0.5 | 0.4 | 0.4 | 0.3 | 0.3 | 0.3 | 0.3 | 0.2 | 0.2 | 0.2
| Nitendo2 | Accessories | Vincent Chen | FIH | [21 empty] | 0.1 | 0.1 | 0.1
| Artari 2 | Accessories | Vincent Chen | FIH | [21 empty] | 0.1 | 0.1 | 0.1
| Swanky | Room bar | Vincent Chen | TBD | [21 empty] | 0.6 | 0.6 | 0.6
Techno Bricks | [Mason]Thermal Performance of Different Materials and Surface Finishes .pptx(Spring and Summer Intern) |  | Vincent Chen | [14 empty] | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.2 | 0.2
| Active Thermal Solution |  | Vincent Chen | [15 empty] | 0.4 | 0.4 | 0.4 | 0.5 | 0.5 | 0.5 | 0.5 | 0.1 | 0.1 | 0.1
[5 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0.9 | 0.9 | 1.2 | 1.1 | 1.1 | 1.1 | 1 | 1 | 0.8 | 1.1 | 1.1 | 1.1
[5 empty] | Room Sys | New | 0.4 / 0.3 | 0.3 | 0.1
[6 empty] | Extension | 0.2 / 0.1 | 0.1 | 0.1
L4B Vision Project Planning | Dread | AIO |  |  | Webcam | New | 0.3 | 0.2 | 0.1
| Artari 2600 | Accessories |  |  |  | Extension | 0.1 | 0.1 | 0.1
| N64 | Accessories
ODM / Alternative Source Project
[7 empty] | PFE | PB1 | PB2
[5 empty] | Room Sys | New | 0.2 / 0.1 | 0.1 | 0.1
[6 empty] | Extension | 0.1 | 0.1 | 0.1
[5 empty] | Webcam | New | 0.2 / 0.1 | 0.1 | 0.1
[6 empty] | Extension | 0.1 | 0.1 | 0.1

## 2024
| Project | Engineer | Vendor | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
B2B | Kiddy (Fireball 2.0) | Sam Kuan | ODM
| Lanky(KONG 2.0) | Sam Kuan | TBD | [12 empty] | 0.1 | 0.1 | 0.1 | 0.1 |  |  | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4
| EEVEE | Sam Kuan | ODM | [12 empty] | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
| Stratos | Sam Kuan | In House | [6 empty] | 0.3 | 0.3 | 0 | 0 | 0 | 0 | 0.1
Logi G | Zhao | Sam Kuan | In House | [12 empty] | 0.2 | 0.1
PWS | Babylon (sustaining) | Sam Kuan | [14 empty] | 0.1
Techno Bricks | Room 2.0 Thermal Request | Sam Kuan | [16 empty] | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2
| Surface temperature limit | Sam Kuan | [23 empty] | 0.1 | 0.1
| QCM8550 2R Model measurement | Sam Kuan | [18 empty] | 0.2 | 0.2 | 0.2 | 0.2 | 0.2
| Thermal Design OPT | Sam Kuan | [13 empty] | 0.2 | 0.1 | 0.1
| Thermal Comfort Jury study | Sam Kuan | [13 empty] | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2
| Virtual skin | Sam Kuan | [13 empty] | 0.1
| Aluminum VC | Sam Kuan | [14 empty] | 0.1 | 0.1 | 0.1 | 0.1
| Solderless Process | Sam Kuan | [14 empty] | 0.1 | 0.1 | 0.1 | 0.1
| Thermal underfill | Sam Kuan | [17 empty] | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
| Airjet | Sam Kuan | [15 empty] | 0.1 | 0.1 | 0.1 | 0.1
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.3 | 0.3 | 0 | 0 | 0 | 0 | 1 | 0.9 | 0.8 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.7 | 0.7
B2B | Lemmy | Vincent Chen | FIH | [12 empty] | 0.4 | 0.4 | 0.4 | 0.4 | 0.3 | 0.3 | 0.1 | 0.1
| Dixie | Vincent Chen | Amtran | [12 empty] | 0.4 | 0.4 | 0.4 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
| Flight | Vincent Chen | In House | [12 empty] | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
| Nitro | Vincent Chen | Bizlink | [12 empty] | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
| Kiddy (Fireball 2.0) | Vincent Chen | ODM
| Goomba (Micpod 2.0) | Vincent Chen | TBD | 0.1 | 0.1 | 0.1 | [18 empty] | 0.1 | 0.3 | 0.3
| Dread(Bolide 2.0) | Vincent Chen | TBD
| Sentinel Next (minor revision) | Vincent Chen | TBD
Techno Bricks | Cold Chamber | Vincent Chen | Therelct | [12 empty] | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
| Anti-sag THM solution | Vincent Chen | Tianmai | [16 empty] | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
| Direct contact | Vincent Chen | Tianmai | [18 empty] | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1 | 1.1 | 1.1 | 1.2 | 1.2 | 1.2 | 1.1 | 0.9 | 0.8 | 0.9 | 1 | 1
In House / JDM Project
[6 empty] | PFE | PB1 | PB2
|  |  |  | Room Sys | New | 0.4 / 0.3 | 0.3 | 0.1
[5 empty] | Extension | 0.2 / 0.1 | 0.1 | 0.1
|  |  |  | Webcam | New | 0.3 | 0.2 | 0.1
[5 empty] | Extension | 0.1 | 0.1 | 0.1
ODM / Alternative Source Project
[6 empty] | PFE | PB1 | PB2
|  |  |  | Room Sys | New | 0.2 / 0.1 | 0.1 | 0.1
[5 empty] | Extension | 0.1 | 0.1 | 0.1
|  |  |  | Webcam | New | 0.2 / 0.1 | 0.1 | 0.1
[5 empty] | Extension | 0.1 | 0.1 | 0.1

## 2023
| Project | Engineer | Vendor | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Room System | KONG 2.0 | Sam Kuan | TBD | 0.1 | 0.1 | 0.1 | [17 empty] | Parental leave
| Tiny | Sam Kuan | FIH | [8 empty] | 0.2 | 0.2 | 0.4 | 0.4 | 0.3 | 0.3 | 0.3 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
| Dixie | Sam Kuan | FIH | [15 empty] | 0.3 | 0.3 | 0.3 | 0.4 | 0.4
| Coily | Sam Kuan | Wistron | 0.2 | 0.2 | 0.2 | 0 | 0 | 0 | 0 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.2 | 0.2 | 0.2 | 0.2 | 0.1 | 0.1 | 0.1 | 0.1
| EEVEE | Sam Kuan | ODM | [23 empty] | 0.2
Webcam | Start 4K | Sam Kuan | In House |  |  |  | 0.3 | 0.3 | 0.3 | 0.2 | 0.2 | 0.2 | 0.2 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
| Stratos | Sam Kuan | In House | [6 empty] | 0.3 | 0.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.2 | 0.2 | 0.2 | 0.1 | 0.1 |  |  | 0.1 | 0.1
Mobility | Spine | Sam Kuan | In House | [16 empty] | 0.2 | 0.2
Logi G | Rogue One | Sam Kuan | In House | [22 empty] | 0.2 | 0.1
Logi G | Zhao | Sam Kuan | TBD | [22 empty] | 0.2 | 0.2
Thermal Techno Bricks | Airjet | Sam Kuan | [21 empty] | 0.1 | 0.1 | 0 | 0
| Thermal sim optimization tool (Cold stream、DoE、SmartDo) | Sam Kuan | [21 empty] | 0.1 | 0.1 | 0.4 | 0.3
| Thermal Comfort Jury study | Sam Kuan | [21 empty] | 0.1 | 0.1 | 0.1 | 0.1
|  |  |  | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.5 | 0.6 | 0.5 | 0.5 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.8 | 0.9 | 0.9 | 0.7 | 0.7 | 0.3 | 0.3 | 1 | 1
Room System | Sentinel | Vincent Chen | FIH | [8 empty] | 0.3 | 0.4 | 0.4 | 0.4 | 0.3 | 0.2 | 0.2 | 0.1 | 0.1
| Lemmy | Vincent Chen | FIH | [13 empty] | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4
| Dixie | Vincent Chen | TBD | [19 empty] | 0.3 | 0.4 | 0.4 | 0.4 | 0.4
| Flight | Vincent Chen | ODM | [19 empty] | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
| EEVEE | Vincent Chen | ODM |  |  | . | [14 empty] | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2
| Nitro | Vincent Chen | ODM | [19 empty] | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
Webcam | Matiee | Vincent Chen | In House | [5 empty] | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
| Ingres | Vincent Chen | In House | [13 empty] | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
| Cezanne | Vincent Chen | In House | [6 empty] | 0.1 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0.1 | 0.2 | 0.3 | 0.6 | 0.7 | 0.7 | 0.7 | 0.5 | 0.9 | 0.9 | 0.8 | 0.8 | 0.9 | 0.9 | 1.1 | 1.2 | 1.2 | 1.2 | 1.2
In House / JDM Project
[6 empty] | PFE | PB1 | PB2
|  |  |  | Room Sys | New | 0.4 / 0.3 | 0.3 | 0.1
[5 empty] | Extension | 0.2 / 0.1 | 0.1 | 0.1
|  |  |  | Webcam | New | 0.3 | 0.2 | 0.1
[5 empty] | Extension | 0.1 | 0.1 | 0.1
ODM / Alternative Source Project
[6 empty] | PFE | PB1 | PB2
|  |  |  | Room Sys | New | 0.2 / 0.1 | 0.1 | 0.1
[5 empty] | Extension | 0.1 | 0.1 | 0.1
|  |  |  | Webcam | New | 0.2 / 0.1 | 0.1 | 0.1
[5 empty] | Extension | 0.1 | 0.1 | 0.1

## 2022
|  |  |  | 2021 | [11 empty] | 2022
| Project | Engineer | Vendor | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
VC Room System | KONG | Sam Kuan | FIH | 0.1 | 0.1 | 0.1
| DIDDY | Sam Kuan | FIH | 0.3 | 0.3 | 0.3 | 0.1 | 0.1 | 0.1
| Candy | Sam Kuan | TBD | [5 empty] | 0.1 | 0.1 | 0.3 | 0.3 | 0.3
| Tiny | Sam Kuan | FIH | [8 empty] | 0.2 | 0.2 | 0.4 | 0.4 | 0.4 | 0.4 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.3 | 0.3 | 0.3 | 0.3
| Qbert | Sam Kuan | Luxshare | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.1 | 0.1 | 0.1
| Qbert Room Kit | Sam Kuan | Luxshare | [15 empty] | 0.2 | 0.2 | 0.2 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
| Coily | Sam Kuan | Wistron | 0.2 | 0.2 | 0.2 | 0 | 0 | 0 | 0 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.3 | 0.3 | 0.2 | 0.2 | 0.2 | 0.1 | 0.1 | 0.1 | 0.1
| Gorochu | Sam Kuan | TBD | [9 empty] | 0.2 | 0.2 | 0.1 | 0.1 | 0.1 | 0.1
VC Webcam | Van Gogh | Sam Kuan | In House |  |  |  | 0.1 | 0.1 | 0.1 | 0.1
| Gauguin | Sam Kuan | In House |  |  |  | 0.3 | 0.3 | 0.3 | 0.2 | 0.2 | 0.2 | 0.2 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
| Stratos | Sam Kuan | In House | [6 empty] | 0.3 | 0.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0.9 | 0.9 | 0.9 | 0.8 | 0.8 | 0.9 | 1 | 1.1 | 1 | 1.2 | 1 | 0.9 | 0.8 | 0.8 | 0.9 | 1 | 1 | 0.9 | 0.8 | 0.8 | 0.5 | 0.5 | 0.5 | 0.5
VC Room System | Sega | Vincent Chen | FIH | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.1 | 0.1 | 0.1
| Nintendo | Vincent Chen | FIH | 0.2 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
| Atari | Vincent Chen | FIH | 0.2 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
| Celestia | Vincent Chen | In House | 0.3 | 0.3 | 0.3 | 0.2 | 0.1 | 0.1
| Sentinel | Vincent Chen | FIH | [8 empty] | 0.3 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.3 | 0.3 | 0.3 | 0.3
| Ditto | Vincent Chen | Intretech | [9 empty] | 0.1 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.1 | 0.1
| SEGA 1.1 | Vincent Chen | TBD |  |  | .
| DIDDY 1.1 | Vincent Chen | TBD
VC Webcam | Locke | Vincent Chen | In House | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
| Hobbes | Vincent Chen | In House |  | 0.1 | 0.1 | 0.1 | 0.1
| Voltaire2 | Vincent Chen | In House |  | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
| HobbesX | Vincent Chen | In House |  |  | 0.1 | 0.1 | 0.2 | 0.2 | 0.2 | 0.1
| Degas | Vincent Chen | Chicony | [5 empty] | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
| Matiee | Vincent Chen | In House | [6 empty] | 0.1 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2
| Warhol | Vincent Chen | In House | [14 empty] | 0.1 | 0.1 | 0.2 | 0.2 | 0.1 | 0.1 | 0 | 0 | 0 | 0
| Cezanne | Vincent Chen | In House | [18 empty] | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2
| Mondrian | Vincent Chen | In House | [7 empty] | 0.1 | 0.2 | 0.2 | 0.2 | 0.2 | 0.1 | 0.1
|  |  |  | 1 | 1 | 1.1 | 1 | 1 | 0.9 | 0.9 | 0.9 | 1 | 1.1 | 1.1 | 1.1 | 1 | 1 | 1 | 0.9 | 1 | 0.9 | 1 | 1 | 0.7 | 0.7 | 0.7 | 0.7
In House / JDM Project
[6 empty] | PFE | PB1 | PB2
|  |  |  | Room Sys | New | 0.4 / 0.3 | 0.3 | 0.1
[5 empty] | Extension | 0.2 / 0.1 | 0.1 | 0.1
|  |  |  | Webcam | New | 0.3 | 0.2 | 0.1
[5 empty] | Extension | 0.1 | 0.1 | 0.1
ODM / Alternative Source Project
[6 empty] | PFE | PB1 | PB2
|  |  |  | Room Sys | New | 0.2 / 0.1 | 0.1 | 0.1
[5 empty] | Extension | 0.1 | 0.1 | 0.1
|  |  |  | Webcam | New | 0.2 / 0.1 | 0.1 | 0.1
[5 empty] | Extension | 0.1 | 0.1 | 0.1

## Sheet14
Project | Category | ODM / JDM | State | Thermal Task | GO Date | Target MP Date
Kiddy | PTZ Camera | Chicony | PB1 | [TB] Thermal simulation of Kiddy wall-mounted box | 2024-12-01 | Q1-2026 (March)
Goomba | Mic | TYNPHANY | PQR |  | 2025-02-01 | Q1-2026 (Jan)
Lanky | Room Bar | AMTRAN | PB1 | [TB] Evaluate the feasibility of integrating an active thermal solution in Lanky. [TB] PCB Thermal resistance improvement | 2025-05-01 | Q2-2026 (June)
Atari/Nintendo | Accessories | FIH | PA1 |  | 2025-08-01 | Q2-2026 (June)
Jolteon | Accessories | TBD | TBD |  | 2025-08-01 | Q4-2025 (Oct)
Kiddo | PTZ Camera | Chicony | RFQ | [TB] Thermal simulation of Kiddo wall-mounted box | 2025-09-01 | Q2-2026 (June)
Arbok | Accessories | INTRETECH | RFQ |  | 2025-09-01 | Q2-2026
Weedle | Accessories | CWT | PA1 | [TB] Weedle Thermal Evaluation | 2025-09-01
Swanky | Room Bar | TBD | Engineering Response | TBD | 2025-10-01 | Q4-2026
Dread/Coleco | AIO Sys | TBD | Engineering Response |  | 2025-10-01 | Q4-2026
Doogan | Accessories | TBD | Engineering Response |  | 2025-10-01 | Q2-2026
Cranky | Table Camera | TBD | Engineering Response | TBD | 2025-11-01 | Q1-2027
Coily-Rebirth | Accessories | TBD | RFQ
Other Mounts | Accessories | TBD | RFQ | TBD
D

## Thermal loading Indicator
Thermal loading Indicator
Resource score | Description | Remark
0.4 ¦ 0.3 | Significant thermal resource requirements, typically for thermal simulations and experiments conducted before molding. | Vision/PFE / PA
0.3 | Thermal hardware validation requirements for performance and manufacturing. | PB
0.2 ¦ 0.1 | Partial thermal validation for low thermal risk and thermal policy optimization. | PB / PQR
0.1 | Limited to thermal parts maintenance only or small accessory project. | Sustaining