## Master Parameter Table
Dixie65 → Hinoki Master Parameter Table
Source-traceable concept inputs only — no CAD generated. Classification vocabulary: Known / Derived / Assumed / TBD.
ID | Category | Parameter | Dixie65 Value | Hinoki Target / Value | Units | Classification | Source Document / File | Page / Section / CAD Feature | Derivation / Rationale | Confidence / Notes | CAD-Driving? | Scaling Treatment | Assumption ID | Consistency / Traceability Check
MP-001 | Product Requirement | Product use case | Large-room 65-inch collaboration display | 32-inch desktop / focus-room all-in-one | — | Known | User request; Dixie and Hinoki table.xlsx | Prompt; Sheet1 row 5 | Hinoki is a new desktop packaging problem; Dixie is an architectural reference. | High | Yes | Do not scale |  | Pass
MP-002 | Panel | Nominal display diagonal | 65 | 32 | in | Known | Dixie and Hinoki table.xlsx; User request | Sheet1 row 5; prompt | Direct product requirement. | High | Yes | Direct requirement |  | Pass
MP-003 | Panel | Resolution | TBD in supplied files | 3840 × 2160 (4K UHD) | pixels | Assumed | User request | Prompt says 4K; exact raster not stated | Use UHD raster as provisional interpretation of 4K. | Medium; confirm whether DCI 4096 × 2160 is excluded. | Yes | Do not scale | A-001 | Open: exact 4K raster requires PRD confirmation
MP-004 | Panel | Display aspect ratio | TBD in supplied files | 16:9 | ratio | Assumed | Hinoki Assumption Log | A-002 | Typical 32-inch UHD conferencing panel format; needed for active-area derivation. | Medium | Yes | Do not scale | A-002 | Pass
MP-005 | Panel | Derived active width | TBD | 708.4 | mm | Derived | MP-002; MP-004 | 32-inch diagonal and assumed 16:9 | 25.4 × 32 × 16 / √(16²+9²). | High conditional on A-002 | Yes | Re-derive | A-002 | Pass
MP-006 | Panel | Derived active height | TBD | 398.5 | mm | Derived | MP-002; MP-004 | 32-inch diagonal and assumed 16:9 | 25.4 × 32 × 9 / √(16²+9²). | High conditional on A-002 | Yes | Re-derive | A-002 | Pass
MP-007 | Panel | Derived pixel pitch | TBD | 0.1845 | mm/pixel | Derived | MP-003; MP-005 | UHD horizontal pixels and derived active width | 708.4 / 3840. | Medium; panel datasheet must supersede. | Yes | Re-derive | A-001; A-002 | Pass
MP-008 | Panel | Touch technology | IR touch frame | Projected capacitive touch | — | Known | Dixie and Hinoki table.xlsx; User request | Sheet1 row 5; prompt | Direct Hinoki requirement; IR frame geometry must not be scaled. | High | Yes | Do not scale |  | Pass
MP-009 | Panel | Top glass / cover lens | 1465.3 × 845.6 × 4; description also states T=3.2 | TBD by selected panel and capacitive stack | mm | TBD | Dixie BOM | Other Parts, Top Glass item | Dixie glass documents AG/AFP/antimicrobial intent, but Hinoki stack dimensions depend on panel/touch vendor. | High for Dixie values; source has thickness inconsistency. | Yes | Re-derive |  | Open: 4 mm dimension conflicts with T=3.2 mm text
MP-010 | Panel | Cover-glass surface treatment | AG / AFP / antimicrobial noted | AG / AFP target; antimicrobial TBD | — | TBD | Dixie BOM; Dixie and Hinoki table.xlsx | Other Parts Top Glass; Sheet1 row 5 | Preserve glare and fingerprint-control philosophy; final coating specification needs optical/touch validation. | Medium | No | Preserve intent |  | Pass
MP-011 | Panel | Stylus | Passive stylus | None | — | Known | Dixie and Hinoki table.xlsx | Sheet1 row 5 | Direct plan-of-record difference. | High | No | Do not scale |  | Pass
MP-012 | Mechanical | Dixie head mass | 42 | TBD | kg | Known | Dixie BOM | Set & Carton sheet, Net (Head) | Reference load only; Hinoki mass must be rebuilt from selected panel, chassis and stand. | High | Yes | Do not scale |  | Pass
MP-013 | Mechanical | Main housing envelope | 14498.4 × 986.8 × 66.2 (source literal) | TBD | mm | Known | Dixie BOM | Plastic Parts List, Main Housing | Source literal is inconsistent with 65-inch product and top-glass width; likely decimal-entry error, so it must not drive Hinoki CAD. | Low for first dimension; high for source transcription. | No | Do not scale |  | Fail: 14498.4 mm conflicts with 1465.3 mm glass width
MP-014 | Mechanical | Rear housing nominal wall thickness | 3.5 | TBD after structure / molding study | mm | Known | Dixie BOM | Plastic Parts List, Main Housing | Dixie molding reference only; smaller enclosure needs its own rib, boss, flatness and tooling analysis. | High | Yes | Re-derive |  | Pass
MP-015 | Industrial Design | Rear housing material strategy | 85% PCR PC/ABS graphite or 50% PCR PC/ABS off-white; V0 | PCR PC/ABS, V0 target; grade and PCR percentage TBD | — | Derived | Dixie BOM | Plastic Parts List, Main Housing | Preserve recycled-material and flame-rating philosophy without locking a grade before structural/thermal qualification. | Medium | Yes | Preserve intent |  | Pass
MP-016 | Industrial Design | Colorways | Graphite / off-white | Graphite / off-white intent; CMF TBD | — | Derived | Dixie BOM | Plastic Parts List, multiple exterior parts | Carry Dixie family language as concept intent. | Medium | No | Preserve intent |  | Pass
MP-017 | Mechanical | Dixie camera-barrel upper cover envelope | 129.8 × 70.8 × 34.9 | TBD | mm | Known | Dixie BOM; 3V65008203A3_CAMERA BARREL UPPER_ASM_PMP_MP.pdf | Plastic Parts List item 21-1; drawing feature | Reference packaging only; Hinoki camera optical path and shutter require re-layout. | High | No | Do not scale |  | Pass
MP-018 | Mechanical | Dixie camera-barrel lower cover envelope | 129.8 × 70.8 × 48.7 | TBD | mm | Known | Dixie BOM; 3V65009203A3_CAMERA BARREL LOWER_ASM_PMP_MP.pdf | Plastic Parts List item 21-2; drawing feature | Reference packaging only. | High | No | Do not scale |  | Pass
MP-019 | Mechanical | Dixie camera glass | 70.75 × 27.24 × 0.7 | TBD | mm | Known | Dixie BOM | Other Parts, CAMERA BARREL GLASS | Optical window dimensions cannot be scaled because lens FOV, sensor and ray clearance change. | High | Yes | Do not scale |  | Pass
MP-020 | Camera | Camera output | Integrated camera; Dixie output not confirmed in supplied files | Integrated 4K camera | — | Known | User request | Prompt | Direct Hinoki requirement. | High | Yes | Direct requirement |  | Pass
MP-021 | Camera | Image sensor | IMX283 | TBD | — | TBD | Dixie and Hinoki table.xlsx | Sheet1 row 3 | Do not inherit sensor until performance, availability, module size, power and thermal data are confirmed. | High for Dixie; open for Hinoki. | Yes | Do not scale |  | Pass
MP-022 | Camera | Horizontal field of view | 110 | 134–140 | deg | Known | Dixie and Hinoki table.xlsx; User request | Sheet1 row 3; prompt | Direct Hinoki optical requirement; higher FOV changes lens, window and privacy-shutter clearance. | High | Yes | Do not scale |  | Pass
MP-023 | Camera | Camera position | Integrated barrel architecture | Top-center integrated position | — | Assumed | Hinoki Assumption Log | A-003 | Top-center supports symmetric framing and front-light layout; verify industrial-design choice. | Medium | Yes | Do not scale | A-003 | Pass
MP-024 | Camera | Privacy shutter actuation | Automatic rotating | Manual | — | Known | Dixie and Hinoki table.xlsx; User request | Sheet1 row 4; prompt | Direct requirement. | High | Yes | Do not scale |  | Pass
MP-025 | Camera | Privacy shutter retention | Rotating mechanism; retention not established | Non-removable captive shutter | — | Known | User request | Prompt | Direct requirement; include end stops and captive retention features. | High | Yes | Do not scale |  | Pass
MP-026 | Camera | Shutter clear aperture / travel | TBD | TBD after lens ray bundle and tolerance stack | mm | TBD | Required derivation | Camera optical stack | No dimension supplied; must be set from 140° FOV worst case, cover-glass spacing and tolerance stack. | Open | Yes | Re-derive |  | Pass
MP-027 | Compute | System-on-module | QC8550 TC SOM | QC7790 SOM | — | Known | Dixie and Hinoki table.xlsx; User request | Sheet1 row 2; prompt | Direct platform requirement. | High | Yes | Do not scale |  | Pass
MP-028 | Compute | System memory | 12 GB LPDDR5X | TBD | GB | TBD | Dixie and Hinoki table.xlsx | Sheet1 row 2 | Hinoki memory capacity must follow platform/Teams workload and SOM SKU. | High for Dixie | No | Do not scale |  | Pass
MP-029 | Audio | Microphone count | 6 front + 2 rear | TBD | count | TBD | Dixie and Hinoki table.xlsx | Sheet1 row 6 | Desktop acoustic geometry and pickup range require a new array design. | High for Dixie | Yes | Do not scale |  | Pass
MP-030 | Audio | Dixie microphone mechanical interfaces | 6 mic tube rubbers; 13 screw rubbers | TBD | count | Known | Dixie BOM | Plastic Parts List, MIC TUBE RUBBER / MIC SCREW RUBBER | Reference isolation and sealing philosophy; quantities do not transfer. | High | No | Do not scale |  | Pass
MP-031 | Audio | Speaker configuration | 2 × 70 mm + 2 × 31 mm | Integrated speakers; count / size / power TBD | — | TBD | Dixie and Hinoki table.xlsx | Sheet1 row 6 | Desktop listening distance and smaller cavity require acoustic re-optimization. | High for Dixie | Yes | Do not scale |  | Pass
MP-032 | Audio | Front acoustic fabric architecture | 1460 × 110 × 13.6 fabric cover; recycled polyester | Integrated front acoustic treatment TBD | mm | Derived | Dixie BOM | Plastic Parts List, FABRIC COVER | Preserve fabric/acoustic transparency and recycled-material intent, not dimensions. | Medium | Yes | Preserve intent |  | Pass
MP-033 | Interface | HDMI input | 1 × HDMI in plus 1 × HDMI out | 1 × HDMI input | count | Known | Dixie and Hinoki table.xlsx; User request | Sheet1 row 7; prompt | Hinoki does not inherit Dixie HDMI output unless separately required. | High | Yes | Do not scale |  | Pass
MP-034 | Interface | USB-A | 3 × USB 3.1 | 2 × USB-A | count | Known | Dixie and Hinoki table.xlsx; User request | Sheet1 row 7; prompt | Direct requirement; exact generation/current TBD. | High | Yes | Do not scale |  | Pass
MP-035 | Interface | USB-C BYOD | 1 × USB 3.1 + DP Alt Mode | 1 × USB-C BYOD with display/data and PD | count | Known | Dixie and Hinoki table.xlsx; User request | Sheet1 row 7; prompt | Direct requirement; USB generation and DP mode need electrical PRD. | High | Yes | Do not scale |  | Pass
MP-036 | Interface | USB-C laptop charging delivered power | TBD | ≥90 | W delivered to laptop | Known | User request | Prompt | Keep this external delivered power separate from product internal dissipation. | High | No | Direct requirement |  | Pass
MP-037 | Interface | Ethernet | Present | Present | port | Known | Dixie and Hinoki table.xlsx; User request | Sheet1 row 7; prompt | Direct requirement; speed/PoE capability TBD. | High | Yes | Do not scale |  | Pass
MP-038 | Interface | 3.5 mm audio output | Present | Present | port | Known | Dixie and Hinoki table.xlsx; User request | Sheet1 row 7; prompt | Direct requirement. | High | Yes | Do not scale |  | Pass
MP-039 | Interface | Serviceability / cable management | Rear I/O service hatch, cable cover, interface rail and cable-management parts | Serviceable I/O and managed BYOD cable path | — | Derived | Dixie BOM; relevant AVTC drawings | Plastic/Metal Parts Lists; service-hatch, cable-cover, interface-rail features | Preserve Dixie service-access philosophy; re-package to desktop reach zones. | Medium | Yes | Preserve architecture |  | Pass
MP-040 | Connectivity | Wi-Fi | Wi-Fi 6 | Wi-Fi 6 | — | Known | Dixie and Hinoki table.xlsx; User request | Sheet1 row 8; prompt | Direct requirement. | High | No | Direct requirement |  | Pass
MP-041 | Connectivity | Bluetooth Low Energy | BLE | BLE | — | Known | Dixie and Hinoki table.xlsx; User request | Sheet1 row 8; prompt | Direct requirement; version TBD. | High | No | Direct requirement |  | Pass
MP-042 | Sensor | Radar presence detection | Environmental radar; holder 59.8 × 18 × 16.3 | Radar presence detection | — | Known | Dixie and Hinoki table.xlsx; Dixie BOM; User request | Sheet1 row 9; Plastic Parts List Radar Holder; prompt | Function is required, but module and field-of-view clearance need selection. | High | Yes | Do not scale |  | Pass
MP-043 | Sensor | Ambient-light sensor | Present | Include provision; final applicability TBD | — | TBD | Dixie and Hinoki table.xlsx; User request | Sheet1 row 9; prompt says if applicable | Reserve optical/mechanical path until product decision. | Medium | Yes | Do not scale |  | Pass
MP-044 | Sensor | Sensor optical / RF keep-out | TBD | TBD by selected radar and ALS modules | mm | TBD | Module datasheets required | Sensor integration | No keep-out dimensions supplied. | Open | Yes | Re-derive |  | Pass
MP-045 | Lighting | Front lighting | None | Integrated front lighting solution | — | Known | Dixie and Hinoki table.xlsx; User request | Sheet1 row 11; prompt | Function is required; photometric target and architecture TBD. | High | Yes | Do not scale |  | Pass
MP-046 | Lighting | Front-light illuminance / CCT / CRI | None | TBD | lux / K / CRI | TBD | Lighting requirements needed | Front-light subsystem | Cannot size optics, LEDs or thermal load until targets are defined. | Open | Yes | Re-derive |  | Pass
MP-047 | Mounting | VESA compatibility | VESA adapter plate architecture; plate 120 × 120 × 7.8 with 4 × M4 threaded holes | VESA compatible; hole pattern TBD | mm | TBD | Dixie BOM; 171202002550_VESA ADAPTER PLATE.pdf; User request | Metal Parts List item 21; prompt | Plate outside dimensions do not prove hole pitch; choose Hinoki VESA pattern from mass/stand/market requirements. | High for plate envelope; open for pitch. | Yes | Do not scale |  | Pass
MP-048 | Mounting | Desktop stand | Legs / cart / VESA | Height- and tilt-adjustable desktop stand | — | Known | Dixie and Hinoki table.xlsx; User request | Sheet1 row 10; prompt | Direct product requirement. | High | Yes | Do not scale |  | Pass
MP-049 | Mounting | Stand height adjustment range | Not applicable / not supplied | TBD | mm | TBD | Ergonomic specification required | Stand kinematics | No range supplied; do not invent. | Open | Yes | Re-derive |  | Pass
MP-050 | Mounting | Stand tilt range | Not applicable / not supplied | TBD | deg | TBD | Ergonomic specification required | Stand kinematics | No range supplied; do not invent. | Open | Yes | Re-derive |  | Pass
MP-051 | Mounting | Stand base footprint | Not applicable / not supplied | TBD | mm | TBD | Packaging / tip-stability study required | Stand base | Must derive from center of gravity, tilt extremes and safety factor. | Open | Yes | Re-derive |  | Pass
MP-052 | Thermal | Primary compute thermal path | QC8550 thermal gel to heatsink and chassis | QC7790 to heat spreader / chassis concept; stack TBD | — | Assumed | Dixie BOM; Hinoki Assumption Log | Other Parts, THERMAL GEL; A-004 | Preserve Dixie dual-path conduction philosophy provisionally, then verify with QC7790 thermal design guide. | Medium | Yes | Preserve architecture | A-004 | Pass
MP-053 | Thermal | Dixie TIM: compute | TMQ-60 thermal gel, quantity 2.5; 8550-to-heatsink and 8550-to-chassis | TBD by gap, pressure and QC7790 package | — | Known | Dixie BOM | Other Parts, THERMAL GEL item | Reference material concept only; quantity unit is unclear in source. | Medium | Yes | Do not scale |  | Open: BOM quantity unit unspecified
MP-054 | Thermal | Dixie TIM: heat pipe | TMA-3510, 45 × 10 × 1.0, 3.5 W/m·K | TBD | mm; W/m·K | Known | Dixie BOM; thermal-pad drawing set | Other Parts thermal item 1; thermal-pad PDFs | Reference interface; Hinoki gap and conductivity require stack-up and heat-flow analysis. | High | Yes | Re-derive |  | Pass
MP-055 | Thermal | Dixie TIM: heatsink to I/O hatch | TMA-8010X, 45 × 40 × 1.7, 8 W/m·K | TBD | mm; W/m·K | Known | Dixie BOM; thermal-pad drawing set | Other Parts thermal item 2; thermal-pad PDFs | Shows Dixie use of enclosure/service hatch as secondary heat spreader. | High | Yes | Preserve architecture |  | Pass
MP-056 | Thermal | Dixie power-board transistor pads | 15 × 15 × 5, K8, qty 3 for Q911/Q914/Q919 | TBD | mm | Known | Dixie BOM; 194719005121_thermal pad.pdf | Other Parts thermal item 7; drawing | Reference only; Hinoki power architecture and gaps differ. | High | Yes | Re-derive |  | Pass
MP-057 | Thermal | Cooling mode | Large chassis / heat spreader architecture; fan status not established | Passive-first concept; fan requirement TBD by thermal validation | — | Assumed | Hinoki Assumption Log | A-005 | Desktop acoustics favor passive operation, but this is not yet a committed requirement. | Low-to-medium | Yes | Re-derive | A-005 | Pass
MP-058 | Power Model | Scenario: Idle | Not supplied | Subsystem inputs TBD | W | TBD | User request | Power-model scenario definition | Model QC7790, panel/backlight, camera standby, audio, sensors, connectivity, conversion losses and auxiliaries separately. | Open | No | Re-derive |  | Pass
MP-059 | Power Model | Scenario: Normal | Not supplied | Subsystem inputs TBD | W | TBD | User request | Power-model scenario definition | Use measured/qualified average loads; do not infer from Dixie geometry. | Open | No | Re-derive |  | Pass
MP-060 | Power Model | Scenario: Teams Call | Not supplied | Subsystem inputs TBD | W | TBD | User request | Power-model scenario definition | Include active camera/ISP, microphones/DSP, speakers, network, SOM workload and display. | Open | No | Re-derive |  | Pass
MP-061 | Power Model | Scenario: Maximum Brightness | Not supplied | Subsystem inputs TBD | W | TBD | User request | Power-model scenario definition | Separate panel logic and maximum backlight power. | Open | No | Re-derive |  | Pass
MP-062 | Power Model | Scenario: Heavy Load | Not supplied | Subsystem inputs TBD | W | TBD | User request | Power-model scenario definition | Use QC7790 sustained power limit plus concurrent peripheral maxima, avoiding impossible peak stacking. | Open | No | Re-derive |  | Pass
MP-063 | Power Model | Scenario: BYOD + 90 W charging | Not supplied | 90 W delivered to laptop plus Hinoki operating load plus PD losses | W | Derived | User request; MP-036 | Power-model boundary rule | Input draw includes laptop-delivered power; Hinoki internal thermal dissipation excludes that 90 W and includes only PD conversion/conduction losses. | High | No | Re-derive |  | Pass
MP-064 | Power Model | USB-C PD efficiency at 90 W | Not supplied | 92% provisional | % | Assumed | Hinoki Assumption Log | A-006 | Temporary model input until PD controller, DC/DC topology and thermal test data are available. | Low-to-medium | No | Re-derive | A-006 | Pass
MP-065 | Power Model | USB-C PD conversion + conduction loss at 90 W delivered | Not supplied | 7.8 | W | Derived | MP-036; MP-064 | 90 / 0.92 − 90 | Only this loss contributes to Hinoki thermal budget, not the delivered 90 W. | Low-to-medium; depends on A-006 | No | Re-derive | A-006 | Pass
MP-066 | Power Model | QC7790 scenario power | QC8550 values not supplied | TBD for every scenario | W | TBD | QC7790 vendor thermal/power data required | Power model input | Need idle, typical call, sustained and peak values at selected operating limits. | Open | No | Do not scale |  | Pass
MP-067 | Power Model | Display panel logic power | Not supplied | TBD for every scenario | W | TBD | Selected panel datasheet required | Power model input | Keep separate from backlight to model brightness scenarios. | Open | No | Do not scale |  | Pass
MP-068 | Power Model | Backlight power | Not supplied | TBD versus brightness | W | TBD | Selected panel datasheet / measurement required | Power model input | Required for Idle, Normal and Maximum Brightness. | Open | No | Do not scale |  | Pass
MP-069 | Power Model | Camera + ISP power | Not supplied | TBD standby / active 4K | W | TBD | Camera module and QC7790 data required | Power model input | Include sensor, serializer/interface and ISP allocation without double counting SOM power. | Open | No | Do not scale |  | Pass
MP-070 | Power Model | Audio power | Not supplied | TBD idle / call / maximum output | W | TBD | Amplifier and speaker selection required | Power model input | Separate amplifier loss from acoustic output assumptions. | Open | No | Do not scale |  | Pass
MP-071 | Power Model | Radar + ambient sensor power | Not supplied | TBD | W | TBD | Module datasheets required | Power model input | Model always-on and active states separately. | Open | No | Do not scale |  | Pass
MP-072 | Power Model | Wi-Fi / BLE / Ethernet power | Not supplied | TBD by traffic state | W | TBD | Module / PHY datasheets required | Power model input | Avoid double counting radios integrated into SOM/module. | Open | No | Do not scale |  | Pass
MP-073 | Power Model | Front-light power | None | TBD by illuminance target and efficiency | W | TBD | Lighting requirements and LED selection required | Power model input | Add as separate load and local thermal source. | Open | No | Do not scale |  | Pass
MP-074 | Power Model | Power-supply / conversion losses excluding USB-C PD | Not supplied | TBD by rail and scenario | W | TBD | Power-tree design required | Power model input | Model AC/DC and point-of-load efficiencies against actual loads. | Open | No | Do not scale |  | Pass
MP-075 | Power Model | Hinoki internal dissipation boundary | Not explicitly documented | Sum of internal electrical loads and conversion/conduction losses; exclude useful power delivered to laptop | W | Derived | User request | Thermal model boundary | Prevents 90 W laptop charging power from being incorrectly added as Hinoki heat. | High | No | Do not scale |  | Pass
MP-076 | Validation | Source-traceability coverage | Dixie table, BOM, STEP and relevant drawing-file index available | Each row cites prompt, workbook sheet/item, drawing or required future datasheet | — | Derived | All supplied source files | Workbook review | Rows based only on requirements cite the prompt; unresolved values cite the missing governing source. | High | No | Not applicable |  | Pass
MP-077 | Validation | Uniform geometric scaling rule | Not applicable | Uniform 32/65 scaling prohibited | — | Known | User request | Prompt | Panel, camera optics, touch, audio, cooling, ports, VESA and stand are independently re-derived. | High | Yes | Do not scale |  | Pass
MP-078 | Thermal Reference | Dixie thermal-model ambient temperature | 40 on model-setup page; 45 in simulation-results table | TBD by Hinoki operating specification | °C | Known | DIXIE热仿真报告_TMV5_20240329.pdf | pp.3 and 9 | Retain both source literals. Hinoki must define its own ambient design point. | High for transcription; source is internally inconsistent. | No | Do not scale |  | Fail: 40°C setup conflicts with 45°C results table
MP-079 | Thermal Reference | Dixie external-surface emissivity | 0.9 | TBD by Hinoki material / finish | — | Known | DIXIE热仿真报告_TMV5_20240329.pdf | p.3, system-model setup | Radiation boundary condition; Hinoki value depends on actual CMF and coating. | High | No | Re-derive |  | Pass
MP-080 | Thermal Reference | U28 junction-to-case resistance Rjc | 5 | Use QC7790 package value | °C/W | Known | DIXIE热仿真报告_TMV5_20240329.pdf | p.3, U28 chip setup | Dixie simulation input only; do not transfer to QC7790. | High | No | Do not scale |  | Pass
MP-081 | Thermal Reference | U28 junction-to-board resistance Rjb | 0.9 | Use QC7790 package value | °C/W | Known | DIXIE热仿真报告_TMV5_20240329.pdf | p.3, U28 chip setup | Dixie simulation input only; do not transfer to QC7790. | High | No | Do not scale |  | Pass
MP-082 | Power Reference | Dixie U28 modeled heat load | 8 | TBD for QC7790 by scenario | W | Known | DIXIE热仿真报告_TMV5_20240329.pdf | p.4, heat-source layout | Reference component load; not a Hinoki scaling basis. | High | No | Do not scale |  | Pass
MP-083 | Power Reference | Dixie U43 modeled heat load | 3.1 | TBD by Hinoki power-tree component | W | Known | DIXIE热仿真报告_TMV5_20240329.pdf | p.4, heat-source layout | Reference component load. | High | No | Do not scale |  | Pass
MP-084 | Power Reference | Dixie PCB distributed heat load | 2 | TBD by Hinoki PCB loss allocation | W | Known | DIXIE热仿真报告_TMV5_20240329.pdf | p.4, heat-source layout | Background PCB heat term shown separately from named components. | Medium; report does not define allocation scope. | No | Do not scale |  | Pass
MP-085 | Power Reference | Dixie BD1 modeled heat load | 3 | TBD | W | Known | DIXIE热仿真报告_TMV5_20240329.pdf | p.5, power heat-source layout | Reference power-board load. | High | No | Do not scale |  | Pass
MP-086 | Power Reference | Dixie BD2 modeled heat load | 3 | TBD | W | Known | DIXIE热仿真报告_TMV5_20240329.pdf | p.5, power heat-source layout | Reference power-board load. | High | No | Do not scale |  | Pass
MP-087 | Power Reference | Dixie Q40 modeled heat load | 2.5 | TBD | W | Known | DIXIE热仿真报告_TMV5_20240329.pdf | p.5, power heat-source layout | Reference power-board load. | High | No | Do not scale |  | Pass
MP-088 | Power Reference | Dixie Q42 modeled heat load | 2.5 | TBD | W | Known | DIXIE热仿真报告_TMV5_20240329.pdf | p.5, power heat-source layout | Reference power-board load. | High | No | Do not scale |  | Pass
MP-089 | Power Reference | Dixie D41 modeled heat load | 1 | TBD | W | Known | DIXIE热仿真报告_TMV5_20240329.pdf | p.5, power heat-source layout | Reference power-board load. | High | No | Do not scale |  | Pass
MP-090 | Power Reference | Dixie D43 modeled heat load | 1 | TBD | W | Known | DIXIE热仿真报告_TMV5_20240329.pdf | p.5, power heat-source layout | Reference power-board load. | High | No | Do not scale |  | Pass
MP-091 | Power Reference | Dixie LED / backlight modeled heat load | 122.4 | TBD from selected 32-inch panel / backlight | W | Known | DIXIE热仿真报告_TMV5_20240329.pdf | p.5, 0.85 W × 144 LEDs | This dominates the reported Dixie load and must be independently re-derived for Hinoki. | High | No | Do not scale |  | Pass
MP-092 | Power Reference | Dixie total explicitly listed modeled heat load | 148.5 | TBD | W | Derived | DIXIE热仿真报告_TMV5_20240329.pdf | pp.4–5 | Sum U28, U43, PCB, BD1, BD2, Q40, Q42, D41, D43 and LED loads. | Medium; assumes PCB 2 W is additive and no listed source is overlapping. | No | Do not scale |  | Open: confirm whether PCB 2 W overlaps named components
MP-093 | Thermal / Ventilation | Dixie rear-housing upper and lower opening size | >600 × 20 | TBD by Hinoki natural-convection analysis | mm | Known | DIXIE热仿真报告_TMV5_20240329.pdf | p.6, enclosure openings | Dixie passive-convection reference; dimensions cannot be scaled uniformly. | High | Yes | Re-derive |  | Pass
MP-094 | Thermal / Ventilation | Dixie vent open-area ratio | >55 | TBD by Hinoki thermal / acoustic / ingress requirements | % | Known | DIXIE热仿真报告_TMV5_20240329.pdf | p.6, enclosure openings | Reference porosity only; Hinoki needs its own vent impedance and safety review. | High | Yes | Re-derive |  | Pass
MP-095 | Thermal Architecture | Dixie compute heat-spreading stack | Heat sink + heat pipe + copper plate + thermal pads coupled to rear housing / mid-frame | Provision equivalent conductive spreading path; exact stack TBD | — | Known | DIXIE热仿真报告_TMV5_20240329.pdf | pp.7–8, thermal solution 2 | Confirms the architecture behind MP-052 and provides a traceable CAD-feature stack. | High | Yes | Preserve architecture |  | Pass
MP-096 | Thermal Result | Dixie U28 case temperature Tc | 55.71 off / 64.72 on, normal gravity; 55.58 off / 58.99 on, reverse gravity | TBD limit and result | °C | Known | DIXIE热仿真报告_TMV5_20240329.pdf | p.9, simulation-results table | Power/LED off/on cases at the report's stated results-table ambient of 45°C. | High; interpretation limited by 40/45°C ambient conflict. | No | Do not scale |  | Open: resolve simulation ambient discrepancy
MP-097 | Thermal Result | Dixie U28 junction temperature Tj | 91.31 off / 101.89 on, normal gravity; 92.84 off / 96.76 on, reverse gravity | TBD QC7790 junction limit and result | °C | Known | DIXIE热仿真报告_TMV5_20240329.pdf | p.9, simulation-results table | Reference junction result only; QC7790 limits and power are different. | High; interpretation limited by ambient conflict. | No | Do not scale |  | Open: resolve simulation ambient discrepancy
MP-098 | Thermal Result | Dixie gravity and source-coupling sensitivity | With power/LED on, reverse gravity lowers U28 about 5°C; enabling power/LED raises U28 Tc about 9°C in normal gravity | Re-test for Hinoki stand tilt and orientation envelope | °C delta | Derived | DIXIE热仿真报告_TMV5_20240329.pdf | p.9, report conclusions | Shows orientation and display/power heat coupling can materially affect compute temperature. | High for report conclusion; not transferable numerically. | Yes | Re-derive |  | Pass
MP-099 | Thermal Result | Dixie rear-housing reported surface-temperature sample range | 44.73–58.34 | TBD touch-temperature limits and result | °C | Known | DIXIE热仿真报告_TMV5_20240329.pdf | p.15, rear-housing surface temperature map | Use as reference evidence that the enclosure participates in heat spreading; not a Hinoki target. | Medium; sampled callouts, not global extrema. | Yes | Do not scale |  | Pass

## Assumption Log
Hinoki Assumption Log
Every provisional assumption is open until its stated closure evidence is available; no assumed dimension is CAD-release authority.
Assumption ID | Category | Assumption / Provisional Value | Units | Why Needed | Affected Master Parameters | Impact if Wrong | Validation / Closure Evidence | Owner | Status | Confidence / Notes
A-001 | Panel | Interpret ‘4K’ as UHD 3840 × 2160 rather than DCI 4096 × 2160 | pixels | Needed to calculate pixel pitch and interface bandwidth. | MP-003; MP-007 | Panel selection, timing and pixel pitch change. | Approved PRD plus selected panel datasheet. | Product / EE | Open | Medium
A-002 | Panel | Use a 16:9 display aspect ratio | ratio | Needed to derive the 32-inch active-area width and height. | MP-004–MP-007 | Active area, bezel, glass, housing and stand geometry change. | Selected 32-inch panel datasheet. | Product / Display EE | Open | Medium
A-003 | Camera / ID | Locate the integrated camera at the top center of the display | — | Creates a concept datum for symmetric framing, shutter and front-light packaging. | MP-023; MP-026; MP-045 | Industrial design, eye line, cable routing and optical occlusion change. | ID concept approval plus camera framing study. | ID / Camera | Open | Medium
A-004 | Thermal | Preserve Dixie’s dual-path conduction concept from SOM to local spreader and metal chassis | — | Provides a starting architecture before QC7790 thermal design data and enclosure stack-up are available. | MP-052–MP-055 | Chassis material, internal stack, service-hatch temperature and cost may change. | QC7790 thermal design guide, CFD/thermal model and prototype test. | Thermal / ME | Open | Medium
A-005 | Thermal / Acoustic | Use passive-first cooling as the concept baseline | — | Focus-room product should minimize fan noise; no fan requirement was supplied. | MP-057; MP-066; MP-074 | A fan, vent area or thicker chassis may be required. | Worst-case thermal model and acoustic target review. | Thermal / Product | Open | Low-to-medium
A-006 | Power | Use 92% end-to-end USB-C PD efficiency at 90 W delivered power | % | Provides a provisional PD loss input while controller, topology, cables and copper path are undefined. | MP-064; MP-065; MP-075 | At 90% loss is 10.0 W; at 95% loss is 4.7 W, materially changing local thermal design. | Selected PD architecture loss analysis and 90 W thermal measurement. | Power EE / Thermal | Open | Low-to-medium
A-007 | Sensor | Reserve an ambient-light-sensor optical path even though applicability is not yet confirmed | — | Avoids blocking later auto-brightness implementation. | MP-043; MP-044 | Bezel/window and sensor PCB may be removed or relocated. | PRD decision and sensor selection. | Product / EE / ID | Open | Medium
A-008 | Industrial Design | Carry Dixie graphite/off-white family intent into Hinoki concept exploration | — | Preserves product-family design language without locking production CMF. | MP-015; MP-016 | Material grade, texture, heat absorption and appearance may change. | CMF approval and material qualification. | ID / CMF | Open | Medium
A-009 | Serviceability | Retain a user/service-accessible rear I/O zone and managed BYOD cable path | — | Dixie architecture shows hatches, covers and an interface rail; desktop use needs reachable, tidy connections. | MP-039 | Housing split, port PCB placement and stand cable routing change. | Use-case mockup and serviceability review. | ME / ID / EE | Open | Medium
A-010 | Mounting | Evaluate 100 × 100 mm VESA as the initial candidate, without committing CAD | mm | Common candidate for 32-inch displays; supplied Dixie plate envelope does not establish its hole pitch. | MP-047–MP-051 | Adapter, stand interface and rear-housing reinforcement change. | Selected panel/chassis mass, applicable VESA standard and stand supplier confirmation. | ME / Product | Open | Low; do not release CAD from this assumption
A-011 | Front Lighting | Treat front lighting as video-fill lighting integrated near the camera, not decorative status lighting | — | The prompt requires a front lighting solution but gives no photometric definition. | MP-045; MP-046; MP-073 | Optics, glare, eye safety, power and thermal loads may differ substantially. | Product lighting requirement: illuminance, distance, CCT, CRI, uniformity and eye-safety limits. | Product / OE / ID | Open | Low-to-medium
A-012 | Power | For the named BYOD scenario, model 90 W as power delivered at the laptop port; any >90 W product capability is a separate maximum-rating case | W | Keeps the scenario definition stable while preserving the ≥90 W requirement. | MP-036; MP-063–MP-065 | Input supply sizing changes if the scenario is later raised above 90 W. | Power PRD defines advertised PD profile and scenario test point. | Power EE / Product | Open | High for model bookkeeping; rating still TBD
A-013 | Architecture | Use a 760 W × 540 H × 80 D mm Hinoki head concept envelope | mm | Defines a contained package boundary before CAD. | MP-001; MP-002; MP-077 | External dimensions, display fit, component layout and stand load change. | Selected panel, mass model, industrial-design approval and CAD review. | ME / ID | Open | Low-to-medium; concept space claim only, not CAD release authority.
A-014 | Panel | Use a 730 W × 420 H × 18 D mm display/touch stack reservation | mm | Reserves selected 32-inch panel, touch, cover lens and local tolerance space. | MP-003–MP-010 | Bezel, front housing, panel mount and thermal path change. | Selected panel drawing, stack-up and mass data. | Display EE / ME | Open | Medium; packaging reservation only.
A-015 | AV / Acoustic | Reserve an 85 mm-high upper AV/acoustic bar | mm | Packages top camera, shutter, speakers, microphones, lighting and sensors. | MP-020–MP-026; MP-030; MP-045 | Top bezel, camera FOV, speaker volume and acoustic performance change. | ID layout, selected components and acoustic review. | ID / Audio / ME | Open | Medium; geometry reservation only.
A-016 | Camera | Use a 120 × 55 × 42 mm camera plus captive-shutter package | mm | Reserves integration volume before lens, sensor and shutter are selected. | MP-020–MP-025 | FOV, shutter travel, top-bar structure and front aperture change. | Camera/shutter supplier drawing and 140° ray study. | Camera / ME | Open | Low-to-medium; must not constrain final optical selection.
A-017 | Audio | Use two upper speaker enclosure reservations, each 170 × 55 × 40 mm | mm | Protects a credible left/right acoustic volume in the upper bar. | MP-030; MP-045 | Audio SPL, volume, grille, microphone isolation and bar geometry change. | Speaker-driver data, acoustic simulation and prototype test. | Audio / ME | Open | Low-to-medium; driver selection remains open.
A-018 | Lighting | Use two front-light module reservations, each 55 × 12 × 15 mm | mm | Places video-fill lighting beside the camera without entering its FOV. | MP-045; MP-046 | Optics, eye safety, glare, thermal load and camera clearance change. | Lighting requirements and selected module drawing. | OE / ID / ME | Open | Low; package and performance are provisional.
A-019 | Compute | Use a 200 × 120 × 32 mm QC7790 SOM plus local-spreader reservation | mm | Claims central compute and conduction-path space before SOM and heatsink data are available. | MP-027; MP-052–MP-055 | PCB layout, thermal solution, VESA stack and rear cover change. | QC7790 SOM drawing, thermal guide and prototype thermal test. | EE / Thermal / ME | Open | Low-to-medium; includes local thermal stack allowance.
A-020 | Interface | Use a 120 × 75 × 24 mm head USB-C interface/protection-board reservation | mm | Keeps high-current head wiring short while PD bulk power remains in the base. | MP-035; MP-036 | Port access, thermal isolation, cable routing and PCB design change. | USB-C controller, connector and cable drawings. | Power EE / ME | Open | Low-to-medium; not the base PD-stage envelope.
A-021 | Interface | Use a 220 × 60 × 24 mm rear I/O-board reservation | mm | Packages HDMI input, Ethernet, audio-out and rear-service I/O. | MP-033–MP-038 | Port cut-outs, service access and cable routing change. | Connector models, board outline and service review. | EE / ME | Open | Medium; user-port locations remain open.
A-022 | Mounting | Use a 180 × 180 × 18 mm VESA-reinforcement reservation | mm | Claims the central reinforcement around the A-010 100 × 100 mm VESA candidate. | MP-047–MP-051 | Stand interface, rear cover, SOM separation and structural load path change. | VESA selection, stand load case and FEA. | ME / Product | Open | Low; 100 × 100 mm remains an unconfirmed candidate.
A-023 | PCB | Use a 260 × 100 × 15 mm main-PCB reservation | mm | Provides a named package volume for carrier electronics and power-to-CAD mapping. | MP-027; MP-033–MP-042 | Connector layout, thermal density and service clearance change. | Carrier-board outline and connector stack-up. | EE / ME | Open | Low; preliminary envelope only.
A-024 | Sensor | Use an 80 × 20 × 10 mm radar module and field-path reservation | mm | Reserves separate front/upper radar packaging and an unobstructed field path. | MP-042 | Radar range, bezel material and AV-bar layout change. | Radar supplier drawing and field-of-view validation. | Sensor EE / ME | Open | Low; module and field angle are not selected.
A-025 | Sensor | Use a 20 × 20 × 10 mm ambient-light-sensor optical-path reservation | mm | Preserves the conditional sensor option without blocking its optical window. | MP-043; MP-044 | Bezel/window, lighting placement and front optical path change. | PRD decision and sensor drawing. | Sensor EE / ID | Open | Low; conditional requirement.
A-026 | Audio | Use two microphone-region reservations, each 20 × 15 × 12 mm | mm | Keeps outer upper-bar microphone paths independent of camera, speakers and lighting. | MP-030 | Acoustic ports, microphone count and sealing change. | Microphone-array design and acoustic validation. | Audio / ME | Open | Low; array configuration is not selected.
A-027 | Connectivity | Use two Wi-Fi/BLE antenna keep-outs, each 60 × 15 × 8 mm | mm | Preserves RF space away from speaker, camera and central metal thermal structure. | MP-040; MP-041 | RF performance and mechanical layout change. | Antenna design, RF simulation and test. | RF / ME | Open | Low; antenna technology not selected.
A-028 | Thermal | Reserve upper and lower vent paths, each 400 × 20 × 10 mm | mm | Keeps a passive-first convection path before airflow analysis. | MP-093–MP-095 | Rear cover, acoustic leakage, thermal performance and safety change. | CFD, acoustic and ingress review. | Thermal / ME | Open | Low; vent geometry is not released.
A-029 | Serviceability | Use a 120 × 75 × 40 mm USB-C cable and service sweep keep-out | mm | Reserves removable-cable and service access around the user-facing USB-C region. | MP-035; MP-036; MP-039 | Port access, cable bend, rear cover and stand routing change. | Selected cable bend radius and service mock-up. | ME / ID | Open | Low; cable definition is open.
A-030 | Power | Use a 360 × 260 × 90 mm desktop-base AC/DC and bulk-PD package reservation | mm | Locates base heat, ballast and cable storage outside the head. | MP-036; MP-063–MP-065 | Stand size, stability, base thermal design and supply rating change. | Power architecture, mass model and stand concept review. | Power EE / ME | Open | Low; base envelope is conceptual.
A-031 | Power | Use panel/backlight internal-dissipation scenario estimates of 6 / 15 / 18 / 30 / 20 / 15 W | W | Creates preliminary Idle / Normal / Teams / Max Brightness / Heavy / BYOD scenarios. | MP-063–MP-065 | Thermal capacity and supply sizing change. | Selected panel electrical and thermal datasheet. | Display EE / Thermal | Open | Low; 30 W maximum is an area-based Dixie reference, not a selected-panel value.
A-032 | Power | Use QC7790 SOM internal-dissipation scenario estimates of 3 / 7 / 9 / 7 / 12 / 7 W | W | Establishes concept thermal loads before QC7790 performance data. | MP-027; MP-063–MP-065 | Compute spreader, venting and thermal limits change. | QC7790 power model and measured workload traces. | EE / Thermal | Open | Low; Dixie QC8550 10 W is reference only.
A-033 | Power | Use preliminary scenario loads for memory, carrier/PMIC, I/O, Wi-Fi/BLE, camera, audio, sensors and lighting as shown in the Preliminary Power Budget | W | Provides complete scenario bookkeeping and a heat-source-to-space-claim map. | MP-033–MP-046; MP-063–MP-065 | Thermal density, power supply and component layout change. | Schematics, BOM, measured rails and subsystem specifications. | EE / Thermal | Open | Low; source-specific values are model inputs, not final requirements.
A-034 | Power | Use 7.8 W USB-C PD internal loss at 90 W laptop delivery based on 92% end-to-end efficiency | W | Keeps laptop-delivered power separate from Hinoki internal heat. | MP-036; MP-064; MP-065 | Base PD thermal design and supply capability change. | Selected PD topology and 90 W thermal measurement. | Power EE / Thermal | Open | Low-to-medium; derived from A-006 and A-012.
A-035 | Stand Kinematics | Use a nominal VESA pivot height of 430 mm above desk with total height travel of 120 mm (370 to 490 mm) | mm | Defines the first adjustable-desktop-stand motion envelope. | MP-048–MP-051 | Desk clearance, eye line, column length, cable routing and center of gravity change. | Ergonomic target, stand-supplier study and CAD motion review. | ME / ID / Product | Open | Assumed; concept CAD only, no ergonomic release.
A-036 | Stand Kinematics | Use tilt states of 5° forward, 0° neutral and 20° rearward about the VESA pivot | deg | Defines three CAD review positions before a mechanism is selected. | MP-048–MP-051 | Camera FOV, desk clearance, stability and hinge packaging change. | Ergonomic study, hinge selection and motion-interference review. | ME / ID / Product | Open | Assumed; sign convention is forward negative and rearward positive.
A-037 | Stand Stability | Use a 500 W × 340 D mm base contact support polygon, extending 140 mm forward and 200 mm rearward of the stand column | mm | Creates a measurable static support polygon for the desktop stand. | MP-048–MP-051 | Tip resistance, desk footprint, base packaging and industrial design change. | Mass model, tip test and industrial-design approval. | ME / ID | Open | Assumed; local stand datum uses Y forward/rearward from column.
A-038 | Stand Stability | Use preliminary masses: head 11.0 kg, moving stand 2.0 kg, base/power/ballast 10.0 kg at Y=+50 mm, and cable 0.5 kg at Y=-20 mm; head CG sweep is ±15 mm in Y | kg; mm | Enables a first static center-of-gravity calculation without selected component masses. | MP-012; MP-048–MP-051 | Base size, ballast, column force and tilt safety change. | Selected panel/chassis/BOM mass properties and tip test. | ME / Power / Product | Open | Low confidence; CAD must retain the mass-property variables.
A-039 | Stand Packaging | Use a 500 W × 340 D × 90 H mm outer base envelope containing the A-030 360 × 260 × 90 mm AC/DC and bulk-PD/ballast package | mm | Makes base power, ballast and cable storage a contained concept package. | MP-036; MP-048–MP-051 | Base appearance, thermal design, stability and cable routing change. | Power architecture, component drawings and stand concept review. | ME / Power EE / ID | Open | Assumed; preserves base-versus-head power split.
A-040 | Stand Stability | Require a preliminary static center-of-gravity margin of at least 75 mm to every front/rear support boundary at neutral and tilt end states | mm | Sets a concept safety screen before dynamic tip testing. | MP-048–MP-051 | Base footprint and ballast may need to increase. | Mass properties, force cases and physical tip test. | ME / Product | Open | Assumed screening criterion; not a compliance or certification limit.

## Frozen Baseline
Hinoki Frozen Baseline | Hinoki Frozen Baseline | Hinoki Frozen Baseline | Hinoki Frozen Baseline | Hinoki Frozen Baseline | Hinoki Frozen Baseline | Hinoki Frozen Baseline | Hinoki Frozen Baseline | Hinoki Frozen Baseline | Hinoki Frozen Baseline | Hinoki Frozen Baseline
Only direct product requirements and source-confirmed Known values are frozen. Assumed, Derived and TBD values remain change-controlled concept inputs. | Only direct product requirements and source-confirmed Known values are frozen. Assumed, Derived and TBD values remain change-controlled concept inputs. | Only direct product requirements and source-confirmed Known values are frozen. Assumed, Derived and TBD values remain change-controlled concept inputs. | Only direct product requirements and source-confirmed Known values are frozen. Assumed, Derived and TBD values remain change-controlled concept inputs. | Only direct product requirements and source-confirmed Known values are frozen. Assumed, Derived and TBD values remain change-controlled concept inputs. | Only direct product requirements and source-confirmed Known values are frozen. Assumed, Derived and TBD values remain change-controlled concept inputs. | Only direct product requirements and source-confirmed Known values are frozen. Assumed, Derived and TBD values remain change-controlled concept inputs. | Only direct product requirements and source-confirmed Known values are frozen. Assumed, Derived and TBD values remain change-controlled concept inputs. | Only direct product requirements and source-confirmed Known values are frozen. Assumed, Derived and TBD values remain change-controlled concept inputs. | Only direct product requirements and source-confirmed Known values are frozen. Assumed, Derived and TBD values remain change-controlled concept inputs. | Only direct product requirements and source-confirmed Known values are frozen. Assumed, Derived and TBD values remain change-controlled concept inputs.
Freeze ID | Master Parameter ID | Category | Approved Parameter | Frozen Value | Units | Basis | Source / Trace | Status | CAD-driving? | Change-Control Note
FB-001 | MP-001 | Product Requirement | Product use case | 32-inch desktop / focus-room all-in-one | — | Known direct requirement | User request; Dixie and Hinoki table.xlsx; Prompt; Sheet1 row 5 | Frozen | Yes | Change requires explicit user approval; do not substitute Dixie geometry.
FB-002 | MP-002 | Panel | Nominal display diagonal | 32 | in | Known direct requirement | Dixie and Hinoki table.xlsx; User request; Sheet1 row 5; prompt | Frozen | Yes | Change requires explicit user approval; do not substitute Dixie geometry.
FB-003 | MP-008 | Panel | Touch technology | Projected capacitive touch | — | Known direct requirement | Dixie and Hinoki table.xlsx; User request; Sheet1 row 5; prompt | Frozen | Yes | Change requires explicit user approval; do not substitute Dixie geometry.
FB-004 | MP-011 | Panel | Stylus | None | — | Known direct requirement | Dixie and Hinoki table.xlsx; Sheet1 row 5 | Frozen | No | Change requires explicit user approval; do not substitute Dixie geometry.
FB-005 | MP-020 | Camera | Camera output | Integrated 4K camera | — | Known direct requirement | User request; Prompt | Frozen | Yes | Change requires explicit user approval; do not substitute Dixie geometry.
FB-006 | MP-022 | Camera | Horizontal field of view | 134–140 | deg | Known direct requirement | Dixie and Hinoki table.xlsx; User request; Sheet1 row 3; prompt | Frozen | Yes | Change requires explicit user approval; do not substitute Dixie geometry.
FB-007 | MP-024 | Camera | Privacy shutter actuation | Manual | — | Known direct requirement | Dixie and Hinoki table.xlsx; User request; Sheet1 row 4; prompt | Frozen | Yes | Change requires explicit user approval; do not substitute Dixie geometry.
FB-008 | MP-025 | Camera | Privacy shutter retention | Non-removable captive shutter | — | Known direct requirement | User request; Prompt | Frozen | Yes | Change requires explicit user approval; do not substitute Dixie geometry.
FB-009 | MP-027 | Compute | System-on-module | QC7790 SOM | — | Known direct requirement | Dixie and Hinoki table.xlsx; User request; Sheet1 row 2; prompt | Frozen | Yes | Change requires explicit user approval; do not substitute Dixie geometry.
FB-010 | MP-033 | Interface | HDMI input | 1 × HDMI input | count | Known direct requirement | Dixie and Hinoki table.xlsx; User request; Sheet1 row 7; prompt | Frozen | Yes | Change requires explicit user approval; do not substitute Dixie geometry.
FB-011 | MP-034 | Interface | USB-A | 2 × USB-A | count | Known direct requirement | Dixie and Hinoki table.xlsx; User request; Sheet1 row 7; prompt | Frozen | Yes | Change requires explicit user approval; do not substitute Dixie geometry.
FB-012 | MP-035 | Interface | USB-C BYOD | 1 × USB-C BYOD with display/data and PD | count | Known direct requirement | Dixie and Hinoki table.xlsx; User request; Sheet1 row 7; prompt | Frozen | Yes | Change requires explicit user approval; do not substitute Dixie geometry.
FB-013 | MP-036 | Interface | USB-C laptop charging delivered power | ≥90 | W delivered to laptop | Known direct requirement | User request; Prompt | Frozen | No | Change requires explicit user approval; do not substitute Dixie geometry.
FB-014 | MP-037 | Interface | Ethernet | Present | port | Known direct requirement | Dixie and Hinoki table.xlsx; User request; Sheet1 row 7; prompt | Frozen | Yes | Change requires explicit user approval; do not substitute Dixie geometry.
FB-015 | MP-038 | Interface | 3.5 mm audio output | Present | port | Known direct requirement | Dixie and Hinoki table.xlsx; User request; Sheet1 row 7; prompt | Frozen | Yes | Change requires explicit user approval; do not substitute Dixie geometry.
FB-016 | MP-040 | Connectivity | Wi-Fi | Wi-Fi 6 | — | Known direct requirement | Dixie and Hinoki table.xlsx; User request; Sheet1 row 8; prompt | Frozen | No | Change requires explicit user approval; do not substitute Dixie geometry.
FB-017 | MP-041 | Connectivity | Bluetooth Low Energy | BLE | — | Known direct requirement | Dixie and Hinoki table.xlsx; User request; Sheet1 row 8; prompt | Frozen | No | Change requires explicit user approval; do not substitute Dixie geometry.
FB-018 | MP-042 | Sensor | Radar presence detection | Radar presence detection | — | Known direct requirement | Dixie and Hinoki table.xlsx; Dixie BOM; User request; Sheet1 row 9; Plastic Parts List Radar Holder; prompt | Frozen | Yes | Change requires explicit user approval; do not substitute Dixie geometry.
FB-019 | MP-045 | Lighting | Front lighting | Integrated front lighting solution | — | Known direct requirement | Dixie and Hinoki table.xlsx; User request; Sheet1 row 11; prompt | Frozen | Yes | Change requires explicit user approval; do not substitute Dixie geometry.
FB-020 | MP-048 | Mounting | Desktop stand | Height- and tilt-adjustable desktop stand | — | Known direct requirement | Dixie and Hinoki table.xlsx; User request; Sheet1 row 10; prompt | Frozen | Yes | Change requires explicit user approval; do not substitute Dixie geometry.
FB-021 | MP-077 | Validation | Uniform geometric scaling rule | Uniform 32/65 scaling prohibited | — | Known direct requirement | User request; Prompt | Frozen | Yes | Change requires explicit user approval; do not substitute Dixie geometry.
FB-022 | MP-043/044 | Sensor | Ambient-light sensor provision | Reserve provision only if applicable | — | Conditional requirement | User requirement; A-007; architecture specification | Conditional | Yes | Do not mandate final sensor or window until product decision.

## Preliminary Power Budget
Hinoki Preliminary Power Budget | Hinoki Preliminary Power Budget | Hinoki Preliminary Power Budget | Hinoki Preliminary Power Budget | Hinoki Preliminary Power Budget | Hinoki Preliminary Power Budget | Hinoki Preliminary Power Budget | Hinoki Preliminary Power Budget | Hinoki Preliminary Power Budget | Hinoki Preliminary Power Budget | Hinoki Preliminary Power Budget | Hinoki Preliminary Power Budget | Hinoki Preliminary Power Budget
Concept internal dissipation only. Laptop-delivered USB-C power is intentionally separated from Hinoki heat. All unselected-component estimates remain Assumed. | Concept internal dissipation only. Laptop-delivered USB-C power is intentionally separated from Hinoki heat. All unselected-component estimates remain Assumed. | Concept internal dissipation only. Laptop-delivered USB-C power is intentionally separated from Hinoki heat. All unselected-component estimates remain Assumed. | Concept internal dissipation only. Laptop-delivered USB-C power is intentionally separated from Hinoki heat. All unselected-component estimates remain Assumed. | Concept internal dissipation only. Laptop-delivered USB-C power is intentionally separated from Hinoki heat. All unselected-component estimates remain Assumed. | Concept internal dissipation only. Laptop-delivered USB-C power is intentionally separated from Hinoki heat. All unselected-component estimates remain Assumed. | Concept internal dissipation only. Laptop-delivered USB-C power is intentionally separated from Hinoki heat. All unselected-component estimates remain Assumed. | Concept internal dissipation only. Laptop-delivered USB-C power is intentionally separated from Hinoki heat. All unselected-component estimates remain Assumed. | Concept internal dissipation only. Laptop-delivered USB-C power is intentionally separated from Hinoki heat. All unselected-component estimates remain Assumed. | Concept internal dissipation only. Laptop-delivered USB-C power is intentionally separated from Hinoki heat. All unselected-component estimates remain Assumed. | Concept internal dissipation only. Laptop-delivered USB-C power is intentionally separated from Hinoki heat. All unselected-component estimates remain Assumed. | Concept internal dissipation only. Laptop-delivered USB-C power is intentionally separated from Hinoki heat. All unselected-component estimates remain Assumed. | Concept internal dissipation only. Laptop-delivered USB-C power is intentionally separated from Hinoki heat. All unselected-component estimates remain Assumed.
Check | Result | Basis | Meaning
Power-to-CAD mapping | Pass | Each heat source maps to SC-ID | Fail if a heat source has no claim.
Source ID | Heat source / function | CAD location / Space Claim | Classification | Idle | Normal | Teams Call | Max Brightness | Heavy Load | BYOD + 90 W | Units | Laptop delivered | Source / Assumption
PB-001 | 32-inch panel / backlight | SC-001 | Assumed | 6 | 15 | 18 | 30 | 20 | 15 | W internal | 0 | A-031; panel not selected
PB-002 | QC7790 SOM | SC-009 | Assumed | 3 | 7 | 9 | 7 | 12 | 7 | W internal | 0 | A-032; Dixie QC8550 is reference only
PB-003 | Memory | SC-009 | Assumed | 0.5 | 1 | 1.5 | 1 | 2 | 1 | W internal | 0 | A-033; memory configuration open
PB-004 | Carrier board / PMIC conversion | SC-010 | Assumed | 1.5 | 3 | 3.5 | 3 | 5 | 3 | W internal | 0 | A-033; Dixie regulator group is reference only
PB-005 | HDMI / USB / Ethernet I/O | SC-012 | Assumed | 1 | 3 | 4 | 3 | 5 | 3 | W internal | 0 | A-033; interface implementation open
PB-006 | Wi-Fi 6 / BLE | SC-016 | Assumed | 0.3 | 1 | 1.5 | 1 | 1.5 | 1 | W internal | 0 | A-033; Dixie Wi-Fi module was 3.825 W reference
PB-007 | 4K camera | SC-003 | Assumed | 0.3 | 1.5 | 3 | 1.5 | 3 | 1.5 | W internal | 0 | A-033; camera module not selected
PB-008 | Audio amplifier / speakers | SC-004; SC-005 | Assumed | 0 | 1 | 2 | 1 | 4 | 1 | W internal | 0 | A-033; Dixie amplifier test used 1 kHz sine, 1/8 W
PB-009 | Radar / ambient sensor | SC-014; SC-015 | Assumed | 0.2 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | W internal | 0 | A-033; selected modules unknown
PB-010 | Front lighting | SC-006; SC-007 | Assumed | 0 | 0 | 4 | 0 | 4 | 0 | W internal | 0 | A-033; lighting specification open
PB-011 | USB-C PD conversion loss | SC-011; base A-030 | Derived | 0 | 0 | 0 | 0 | 0 | 7.8 | W internal | 90 | A-034; 90/0.92 - 90
Total by scenario |  |  |  | 12.8 | 33 | 47 | 48 | 57 | 40.8 | W internal | 90 | BYOD external delivery is excluded from internal heat.
BYOD device power demand | 130.8 | W | Internal 40.8 W + laptop-delivered 90 W; concept DC capability before margin.
20% concept sizing margin | 156.96 | W | Concept evaluation only; final supply rating requires power architecture.

## Internal Space Claim
Hinoki Internal Space-Claim Register v0.1 | Hinoki Internal Space-Claim Register v0.1 | Hinoki Internal Space-Claim Register v0.1 | Hinoki Internal Space-Claim Register v0.1 | Hinoki Internal Space-Claim Register v0.1 | Hinoki Internal Space-Claim Register v0.1 | Hinoki Internal Space-Claim Register v0.1 | Hinoki Internal Space-Claim Register v0.1 | Hinoki Internal Space-Claim Register v0.1 | Hinoki Internal Space-Claim Register v0.1 | Hinoki Internal Space-Claim Register v0.1 | Hinoki Internal Space-Claim Register v0.1 | Hinoki Internal Space-Claim Register v0.1 | Hinoki Internal Space-Claim Register v0.1 | Hinoki Internal Space-Claim Register v0.1 | Hinoki Internal Space-Claim Register v0.1 | Hinoki Internal Space-Claim Register v0.1 | Hinoki Internal Space-Claim Register v0.1 | Hinoki Internal Space-Claim Register v0.1
Pre-CAD packaging register. Values are Assumed reservations, not released dimensions. Datum: head center; X right, Y up, Z rearward; head envelope from front Z=0 to rear Z=80 mm. | Pre-CAD packaging register. Values are Assumed reservations, not released dimensions. Datum: head center; X right, Y up, Z rearward; head envelope from front Z=0 to rear Z=80 mm. | Pre-CAD packaging register. Values are Assumed reservations, not released dimensions. Datum: head center; X right, Y up, Z rearward; head envelope from front Z=0 to rear Z=80 mm. | Pre-CAD packaging register. Values are Assumed reservations, not released dimensions. Datum: head center; X right, Y up, Z rearward; head envelope from front Z=0 to rear Z=80 mm. | Pre-CAD packaging register. Values are Assumed reservations, not released dimensions. Datum: head center; X right, Y up, Z rearward; head envelope from front Z=0 to rear Z=80 mm. | Pre-CAD packaging register. Values are Assumed reservations, not released dimensions. Datum: head center; X right, Y up, Z rearward; head envelope from front Z=0 to rear Z=80 mm. | Pre-CAD packaging register. Values are Assumed reservations, not released dimensions. Datum: head center; X right, Y up, Z rearward; head envelope from front Z=0 to rear Z=80 mm. | Pre-CAD packaging register. Values are Assumed reservations, not released dimensions. Datum: head center; X right, Y up, Z rearward; head envelope from front Z=0 to rear Z=80 mm. | Pre-CAD packaging register. Values are Assumed reservations, not released dimensions. Datum: head center; X right, Y up, Z rearward; head envelope from front Z=0 to rear Z=80 mm. | Pre-CAD packaging register. Values are Assumed reservations, not released dimensions. Datum: head center; X right, Y up, Z rearward; head envelope from front Z=0 to rear Z=80 mm. | Pre-CAD packaging register. Values are Assumed reservations, not released dimensions. Datum: head center; X right, Y up, Z rearward; head envelope from front Z=0 to rear Z=80 mm. | Pre-CAD packaging register. Values are Assumed reservations, not released dimensions. Datum: head center; X right, Y up, Z rearward; head envelope from front Z=0 to rear Z=80 mm. | Pre-CAD packaging register. Values are Assumed reservations, not released dimensions. Datum: head center; X right, Y up, Z rearward; head envelope from front Z=0 to rear Z=80 mm. | Pre-CAD packaging register. Values are Assumed reservations, not released dimensions. Datum: head center; X right, Y up, Z rearward; head envelope from front Z=0 to rear Z=80 mm. | Pre-CAD packaging register. Values are Assumed reservations, not released dimensions. Datum: head center; X right, Y up, Z rearward; head envelope from front Z=0 to rear Z=80 mm. | Pre-CAD packaging register. Values are Assumed reservations, not released dimensions. Datum: head center; X right, Y up, Z rearward; head envelope from front Z=0 to rear Z=80 mm. | Pre-CAD packaging register. Values are Assumed reservations, not released dimensions. Datum: head center; X right, Y up, Z rearward; head envelope from front Z=0 to rear Z=80 mm. | Pre-CAD packaging register. Values are Assumed reservations, not released dimensions. Datum: head center; X right, Y up, Z rearward; head envelope from front Z=0 to rear Z=80 mm. | Pre-CAD packaging register. Values are Assumed reservations, not released dimensions. Datum: head center; X right, Y up, Z rearward; head envelope from front Z=0 to rear Z=80 mm.
Head envelope W | Head envelope H | Head envelope D | Hard-package minimum clearance |  | Containment | Hard-package collision
760 | 540 | 80 | 5 |  | Pass | Pass
Claim ID | Zone | Claim Type | Module | Qty | Center X | Center Y | Center Z | W | H | D | Unit Volume | Total Volume | Containment | Clearance / Check | Source MP IDs | Assumption IDs | CAD-driving? | Notes
SC-001 | Front | Hard package | Display + touch stack | 1 | 0 | 0 | 9 | 730 | 420 | 18 | 5518800 | 5518800 | Pass | Pass | MP-002–MP-010 | A-014 | Yes | Panel selection required before release.
SC-002 | Upper | Keep-out | Upper AV / acoustic bar | 1 | 0 | 227.5 | 40 | 760 | 85 | 80 | 5168000 | 5168000 | Pass | Keep-out | MP-020–MP-046 | A-015 | Yes | Zone overlaps its contained top-bar packages by intent.
SC-003 | Upper center | Hard package | 4K camera + manual shutter | 1 | 0 | 225 | 44 | 120 | 55 | 42 | 277200 | 277200 | Pass | Pass | MP-020–MP-025 | A-016 | Yes | Camera optical axis on X=0; protect 140° FOV.
SC-004 | Upper left | Hard package | Upper speaker — left | 1 | -252 | 225 | 43 | 170 | 55 | 40 | 374000 | 374000 | Pass | Pass | MP-030 | A-017 | Yes | Independent upper enclosure.
SC-005 | Upper right | Hard package | Upper speaker — right | 1 | 252 | 225 | 43 | 170 | 55 | 40 | 374000 | 374000 | Pass | Pass | MP-030 | A-017 | Yes | Independent upper enclosure.
SC-006 | Upper left | Hard package | Front light — left | 1 | -97.5 | 225 | 12.5 | 55 | 12 | 15 | 9900 | 9900 | Pass | Pass | MP-045; MP-046 | A-018 | Yes | Maintain 140° camera-FOV keep-out.
SC-007 | Upper right | Hard package | Front light — right | 1 | 97.5 | 225 | 12.5 | 55 | 12 | 15 | 9900 | 9900 | Pass | Pass | MP-045; MP-046 | A-018 | Yes | Maintain 140° camera-FOV keep-out.
SC-008 | Upper outer | Keep-out | Microphone regions — left/right | 2 | -145 | 245 | 6 | 20 | 15 | 12 | 3600 | 7200 | Pass | Keep-out | MP-030 | A-026 | Yes | Mirrored location; protect forward acoustic path.
SC-009 | Central rear | Hard package | QC7790 SOM + heat spreader | 1 | 0 | 0 | 39 | 200 | 120 | 32 | 768000 | 768000 | Pass | Pass | MP-027; MP-052–MP-055 | A-019 | Yes | Conduction path to mid-frame/rear structure.
SC-010 | Lower central rear | Hard package | Main PCB | 1 | 0 | -125 | 47.5 | 260 | 100 | 15 | 390000 | 390000 | Pass | Pass | MP-027; MP-033–MP-042 | A-023 | Yes | Carrier electronics reservation.
SC-011 | Lower right rear | Hard package | USB-C interface / protection PCB | 1 | 260 | -205 | 52 | 120 | 75 | 24 | 216000 | 216000 | Pass | Pass | MP-035; MP-036 | A-020 | Yes | Bulk PD stays in stand base.
SC-012 | Lower rear | Hard package | Rear I/O PCB | 1 | 0 | -210 | 60 | 220 | 60 | 24 | 316800 | 316800 | Pass | Pass | MP-033–MP-038 | A-021 | Yes | Service I/O accessible from rear cover.
SC-013 | Central rear | Structural | VESA reinforcement | 1 | 0 | 0 | 71 | 180 | 180 | 18 | 583200 | 583200 | Pass | Pass | MP-047–MP-051 | A-022; A-010 | Yes | 100 × 100 pattern is still assumed.
SC-014 | Upper right | Keep-out | Radar module / field path | 1 | 145 | 252 | 5 | 80 | 20 | 10 | 16000 | 16000 | Pass | Keep-out | MP-042 | A-024 | Yes | Separate forward sensor field path.
SC-015 | Upper left | Keep-out | Ambient-light sensor path | 1 | -145 | 252 | 5 | 20 | 20 | 10 | 4000 | 4000 | Pass | Keep-out | MP-043; MP-044 | A-025 | Yes | Conditional product feature.
SC-016 | Rear left/right | Keep-out | Wi-Fi / BLE antenna keep-outs | 2 | -340 | 0 | 76 | 60 | 15 | 8 | 7200 | 14400 | Pass | Keep-out | MP-040; MP-041 | A-027 | Yes | Mirrored location; preserve RF clearance.
SC-017 | Upper/lower rear | Keep-out | Vent paths | 2 | 0 | 250 | 75 | 400 | 20 | 10 | 80000 | 160000 | Pass | Keep-out | MP-093–MP-095 | A-028 | Yes | Mirrored upper/lower passive-convection path.
SC-018 | Lower right | Keep-out | USB-C cable / service sweep | 1 | 260 | -205 | 40 | 120 | 75 | 40 | 360000 | 360000 | Pass | Review | MP-035; MP-036; MP-039 | A-029 | Yes | Replace with selected cable bend radius.
Metric | Result
Head envelope volume | 32832000
Hard-package claim volume | 8254600
Approx. envelope reserve ratio | 74.86%

## Stand & Stability
Hinoki Stand & Stability Baseline v0.2
Controlled concept assumptions for desktop-stand travel, tilt, footprint and static center of gravity. These values enable concept CAD only and are not released dimensions.
Parameter | Value | Unit | Assumption ID |  | State | Head CG Y | Total Mass | Assembly CG Y | Front Margin | Rear Margin | Side Margin | Status | Basis
Nominal VESA pivot height | 430 | mm above desk | A-035 |  | Forward tilt | -15 | 23.5 | 13.8298 | 153.8298 | 186.1702 | 250 | Pass | A-036; A-038
Total height travel | 120 | mm | A-035 |  | Neutral | 0 | 23.5 | 20.8511 | 160.8511 | 179.1489 | 250 | Pass | A-035; A-038
Low pivot height | 370 | mm above desk | A-035 |  | Rearward tilt | 15 | 23.5 | 27.8723 | 167.8723 | 172.1277 | 250 | Pass | A-036; A-038
High pivot height | 490 | mm above desk | A-035
Forward tilt | -5 | deg | A-036
Rearward tilt | 20 | deg | A-036
Base width | 500 | mm | A-037; A-039
Base depth | 340 | mm | A-037; A-039
Front support boundary | -140 | mm from column | A-037
Rear support boundary | 200 | mm from column | A-037
Base height | 90 | mm | A-039
Head mass | 11 | kg | A-038
Moving-stand mass | 2 | kg | A-038
Base / power / ballast mass | 10 | kg | A-038
Representative cable mass | 0.5 | kg | A-038
Minimum static CG margin | 75 | mm | A-040
Stand / base space-claim register — local datum: column center at desk plane; X = left/right, Y = rearward, Z = upward.
Claim ID | Element | Type | Center X | Center Y | Center Z | W | D | H | State | Assumption ID | Containment / check | CAD-driving? | Notes
SS-001 | Base contact support polygon | Support | 0 | 30 | 0 | 500 | 340 | 0 | All | A-037 | Pass | Yes | Y limits are -140 / +200 mm from column.
SS-002 | Outer base envelope | Hard package | 0 | 30 | 45 | 500 | 340 | 90 | All | A-039 | Pass | Yes | Contains power, ballast and cable storage.
SS-003 | AC/DC + bulk PD + ballast | Hard package | 0 | 30 | 45 | 360 | 260 | 90 | All | A-030; A-039 | Pass | Yes | Inside SS-002 by intent.
SS-004 | Height-column sweep | Swept keep-out | 0 | 0 | 290 | 100 | 80 | 400 | Low to High | A-035 | Pass | Yes | Covers low/high VESA pivot positions.
SS-005 | VESA pivot / carrier | Structural | 0 | 0 | 430 | 220 | 80 | 220 | All tilt states | A-035; A-036 | Pass | Yes | Must interface to head SC-013.
SS-006 | Head height/tilt sweep | Swept keep-out | 0 | 0 | 430 | 760 | 80 | 660 | Low/high; all tilt | A-035; A-036 | Pass | Yes | Use for desk/base/cable non-interference in CAD.